## Gantt
Natural-Language Control of a Sub-250g Drone — Planned vs Actual Gantt (50 Working Days)
Each task has two layers: PLAN (top) and ACTUAL (bottom). Edit the BLUE cells — on Plan rows: Strand, Effort, Start, End, Gate; on Actual rows: hours spent, actual Start and End. Everything else updates itself.
| Current project day → yellow box (1–50) |  |  |  |  | drives the amber in-progress bars and the gold header marker
Ref | Task | Layer | Strand | Effort (hrs) | Start Day | End Day | Dur (days) | Var (days) | Gate | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
HARDWARE / CONTROL STRAND (critical path)
T1 | Requirements, architecture & BOM | Plan | Summary | 20 | 1 | 5 | 5
T1 | actual | Actual | Summary | 20 | 1 | 5 | 5 | 0
T1.1 | Finalise system & software block diagrams | Plan | Critical | 6 | 1 | 2 | 2
T1.1 | actual | Actual | Critical | 6 | 1 | 2 | 2 | 0
T1.2 | Finalise BOM, check budget, place orders | Plan | Critical | 6 | 2 | 3 | 2
T1.2 | actual | Actual | Critical | 6 | 2 | 3 | 2 | 0
T1.3 | Risk assessment form + book indoor test space | Plan | Critical | 4 | 4 | 4 | 1
T1.3 | actual | Actual | Critical | 4 | 4 | 4 | 1 | 0
T1.4 | Supervisor review of Project Outline | Plan | Critical | 4 | 5 | 5 | 1 |  | G1 | bar: Week 1 1 to Week 10 50
T1.4 | actual | Actual | Critical | 4 | 5 | 5 | 1 | 0
T5 | Build & configure drone | Plan | Summary | 30 | 6 | 15 | 10
T5 | actual | Actual | Summary | 8 | 6
T5.1 | Print Synthara remix frame + top deck (Bambu X1, PETG) | Plan | Critical | 4 | 6 | 7 | 2
T5.1 | actual | Actual | Critical | 8 | 6 | 7 | 2 | 0
T5.2 | Bench test stack + motors (props off, Betaflight) | Plan | Critical | 6 | 6 | 8 | 3
T5.2 | actual | Actual | Critical
T5.3 | Flash ArduPilot (speedybeef4v4) + base config | Plan | Critical | 5 | 9 | 10 | 2
T5.3 | actual | Actual | Critical
T5.4 | MTF-01 bench test on UART3 (mav-apm) | Plan | Critical | 4 | 10 | 11 | 2
T5.4 | actual | Actual | Critical
T5.5 | ESP32 DroneBridge flash + MAVLink-over-WiFi test | Plan | Critical | 5 | 11 | 12 | 2
T5.5 | actual | Actual | Critical
T5.6 | Final assembly; weigh AUW, check balance (CG) | Plan | Critical | 6 | 13 | 15 | 3
T5.6 | actual | Actual | Critical
T6 | Manual hover testing (laptop/joystick over MAVLink) | Plan | Summary | 15 | 16 | 20 | 5
T6 | actual | Actual | Summary | 0
T6.1 | Pre-flight checks: failsafes + disarm kill-switch test | Plan | Critical | 4 | 16 | 16 | 1
T6.1 | actual | Actual | Critical
T6.2 | Tethered first hover (Stabilize / AltHold) | Plan | Critical | 6 | 17 | 18 | 2
T6.2 | actual | Actual | Critical
T6.3 | Basic PID tune + log review | Plan | Critical | 5 | 19 | 20 | 2 |  | G2 | bar: Week 4 20
T6.3 | actual | Actual | Critical
T7 | Optical-flow position hold (highest risk) | Plan | Summary | 30 | 21 | 30 | 10
T7 | actual | Actual | Summary | 0
T7.1 | EKF setup for flow + rangefinder (no GPS), sensor offsets | Plan | Critical | 6 | 21 | 22 | 2
T7.1 | actual | Actual | Critical
T7.2 | Optical-flow calibration flight + scale factors | Plan | Critical | 8 | 23 | 25 | 3
T7.2 | actual | Actual | Critical
T7.3 | Loiter position-hold trials + tuning | Plan | Critical | 12 | 26 | 29 | 4
T7.3 | actual | Actual | Critical
T7.4 | Repeatability: 5 hold trials, record drift | Plan | Critical | 4 | 30 | 30 | 1 |  | G4 | bar: Week 1 1 to Week 10 50
T7.4 | actual | Actual | Critical
T8 | NLP-to-drone integration | Plan | Summary | 15 | 31 | 35 | 5
T8 | actual | Actual | Summary | 0
T8.1 | Single voice commands on real drone (tethered) | Plan | Critical | 6 | 31 | 32 | 2
T8.1 | actual | Actual | Critical
T8.2 | Command sequence: take off, move 1 m, land | Plan | Critical | 9 | 33 | 35 | 3 |  | G5 | bar: Week 1 1 to Week 10 50
T8.2 | actual | Actual | Critical
SOFTWARE / NLP STRAND (parallel)
T2 | SITL & pymavlink setup | Plan | Summary | 12 | 3 | 8 | 6
T2 | actual | Actual | Summary | 5 | 8
T2.1 | Install ArduPilot SITL + QGroundControl / MAVProxy | Plan | Parallel | 5 | 8 | 8 | 1
T2.1 | actual | Actual | Parallel | 5 | 8 | 8 | 1 | 0
T2.2 | pymavlink script: arm, take off, land | Plan | Parallel | 7 | 3 | 5 | 3
T2.2 | actual | Actual | Parallel
T3 | Speech-to-text + rule-based parser | Plan | Summary | 25 | 6 | 15 | 10
T3 | actual | Actual | Summary | 0
T3.1 | Define command grammar + 30-command test corpus | Plan | Parallel | 5 | 6 | 7 | 2
T3.1 | actual | Actual | Parallel
T3.2 | Whisper vs Vosk: word error rate on corpus | Plan | Parallel | 8 | 8 | 10 | 3
T3.2 | actual | Actual | Parallel
T3.3 | Rule-based intent parser (takeoff/move/rotate/hold/land) | Plan | Parallel | 8 | 11 | 13 | 3
T3.3 | actual | Actual | Parallel
T3.4 | Live mic -> intent end-to-end test | Plan | Parallel | 4 | 14 | 15 | 2
T3.4 | actual | Actual | Parallel
T4 | NLP to MAVLink in simulation | Plan | Summary | 18 | 16 | 20 | 5
T4 | actual | Actual | Summary | 0
T4.1 | Command validator + safety limits | Plan | Parallel | 6 | 16 | 17 | 2
T4.1 | actual | Actual | Parallel
T4.2 | Intent -> MAVLink guided-mode mapping | Plan | Parallel | 8 | 17 | 19 | 3
T4.2 | actual | Actual | Parallel
T4.3 | Spoken command drives SITL flight end-to-end | Plan | Parallel | 4 | 20 | 20 | 1 |  | G3 | bar: Week 4 20
T4.3 | actual | Actual | Parallel
T9 | LLM parser + comparative evaluation | Plan | Summary | 20 | 31 | 40 | 10
T9 | actual | Actual | Summary | 0
T9.1 | LLM-based parser behind the same interface | Plan | Parallel | 8 | 31 | 34 | 4
T9.1 | actual | Actual | Parallel
T9.2 | Compare parsers: accuracy, latency, robustness | Plan | Parallel | 8 | 35 | 38 | 4
T9.2 | actual | Actual | Parallel
T9.3 | Results tables + plots for the report | Plan | Parallel | 4 | 39 | 40 | 2
T9.3 | actual | Actual | Parallel
ALL STRANDS
T10 | Final testing, data & report | Plan | Summary | 25 | 36 | 50 | 15
T10 | actual | Actual | Summary | 0
T10.1 | Movement-accuracy trials against floor markers | Plan | Critical | 6 | 36 | 39 | 4
T10.1 | actual | Actual | Critical
T10.2 | End-to-end latency measurement (voice -> motion) | Plan | Critical | 4 | 40 | 41 | 2
T10.2 | actual | Actual | Critical
T10.3 | Write report: method, results, evaluation | Plan | Critical | 12 | 42 | 48 | 7
T10.3 | actual | Actual | Critical
T10.4 | Final review + submission prep | Plan | Critical | 3 | 49 | 50 | 2
T10.4 | actual | Actual | Critical
| TOTAL — planned hours / planned finish day |  |  | 210 |  | 50
| TOTAL — actual hours logged / latest actual finish day |  |  | 33 |  | 8
Legend
Plan — task summary
Plan — hardware / control strand (critical path)
Plan — software / NLP strand (parallel)
Actual — days worked within the plan
Actual — days past the planned end (overrun)
Actual — in progress, up to the current day
Current project day (header)
◆ | Decision gate — sits on the gated subtask's planned end day
Example (illustration only): planned days 3–6, actually took days 3–8
Plan | bar: Week 1 3 to Week 2 6
Actual (Var = +2) | bar: Week 1 3 to Week 2 8

## Task Details
Task Breakdown — planned vs actual (dates and hours link to the Gantt sheet)
Ref | Parent | Task | Strand | Plan hrs | Plan start | Plan end | Actual hrs | Actual start | Actual end | Var (days) | Status | Measurable outcome (verification) | Depends on / notes
T1.1 | T1 | Finalise system & software block diagrams | Critical | 6 | 1 | 2 | 6 | 1 | 2 | 0 | Done — on time | Figures 1-2 agreed with supervisor
T1.2 | T1 | Finalise BOM, check budget, place orders | Critical | 6 | 2 | 3 | 6 | 2 | 3 | 0 | Done — on time | All parts ordered; cost sheet within budget | Battery + charger still to buy
T1.3 | T1 | Risk assessment form + book indoor test space | Critical | 4 | 4 | 4 | 4 | 4 | 4 | 0 | Done — on time | RA form signed; lab space confirmed
T1.4 | T1 | Supervisor review of Project Outline | Critical | 4 | 5 | 5 | 4 | 5 | 5 | 0 | Done — on time | Outline approved (Gate G1) | T1.1-T1.3
T5.1 | T5 | Print Synthara remix frame + top deck (Bambu X1, PETG) | Critical | 4 | 6 | 7 | 8 | 6 | 7 | 0 | Done — on time | Frame printed, supports cleaned, frame <= 55g | STL files from Drone_CAD/Synthara_Remix
T5.2 | T5 | Bench test stack + motors (props off, Betaflight) | Critical | 6 | 6 | 8 |  |  |  |  | Not started | Smoke test passed; all 4 motors spin, order/direction correct | Bench PSU 11.1V, current-limited
T5.3 | T5 | Flash ArduPilot (speedybeef4v4) + base config | Critical | 5 | 9 | 10 |  |  |  |  | Not started | Quad X, DShot600, accel cal, battery reads within 0.1V | T5.2
T5.4 | T5 | MTF-01 bench test on UART3 (mav-apm) | Critical | 4 | 10 | 11 |  |  |  |  | Not started | Range within a few cm at 0.2/0.5/1 m; flow responds X/Y | T5.3
T5.5 | T5 | ESP32 DroneBridge flash + MAVLink-over-WiFi test | Critical | 5 | 11 | 12 |  |  |  |  | Not started | QGroundControl connects to the FC over WiFi | ESP32 WROOM-32D; avoid 9V pin on VTX port
T5.6 | T5 | Final assembly; weigh AUW, check balance (CG) | Critical | 6 | 13 | 15 |  |  |  |  | Not started | AUW < 250g (target ~203g); CG within 5mm of centre | 3S packs + charger bought; T5.1-T5.5
T6.1 | T6 | Pre-flight checks: failsafes + disarm kill-switch test | Critical | 4 | 16 | 16 |  |  |  |  | Not started | Laptop disarm stops motors instantly; battery failsafe set | T5.6
T6.2 | T6 | Tethered first hover (Stabilize / AltHold) | Critical | 6 | 17 | 18 |  |  |  |  | Not started | 30 s stable tethered hover, no oscillation | Prop guards fitted
T6.3 | T6 | Basic PID tune + log review | Critical | 5 | 19 | 20 |  |  |  |  | Not started | Stable hover recorded on video (Gate G2)
T7.1 | T7 | EKF setup for flow + rangefinder (no GPS), sensor offsets | Critical | 6 | 21 | 22 |  |  |  |  | Not started | EKF healthy on bench; FLOW_POS_X set (~0.041 m) | T5.4
T7.2 | T7 | Optical-flow calibration flight + scale factors | Critical | 8 | 23 | 25 |  |  |  |  | Not started | Flow rates match gyro rates in logs
T7.3 | T7 | Loiter position-hold trials + tuning | Critical | 12 | 26 | 29 |  |  |  |  | Not started | Drift < 0.5 m over 30 s
T7.4 | T7 | Repeatability: 5 hold trials, record drift | Critical | 4 | 30 | 30 |  |  |  |  | Not started | 5/5 trials < 0.5 m drift (Gate G4)
T8.1 | T8 | Single voice commands on real drone (tethered) | Critical | 6 | 31 | 32 |  |  |  |  | Not started | Takeoff / hold / land each work from voice | T4.3, T7.4
T8.2 | T8 | Command sequence: take off, move 1 m, land | Critical | 9 | 33 | 35 |  |  |  |  | Not started | Sequence executed from voice (Gate G5)
T2.1 | T2 | Install ArduPilot SITL + QGroundControl / MAVProxy | Parallel | 5 | 8 | 8 | 5 | 8 | 8 | 0 | Done — on time | Simulated copter arms and flies
T2.2 | T2 | pymavlink script: arm, take off, land | Parallel | 7 | 3 | 5 |  |  |  |  | Not started | Scripted flight completes in SITL
T3.1 | T3 | Define command grammar + 30-command test corpus | Parallel | 5 | 6 | 7 |  |  |  |  | Not started | Corpus file with expected intents and parameters
T3.2 | T3 | Whisper vs Vosk: word error rate on corpus | Parallel | 8 | 8 | 10 |  |  |  |  | Not started | WER table for both engines
T3.3 | T3 | Rule-based intent parser (takeoff/move/rotate/hold/land) | Parallel | 8 | 11 | 13 |  |  |  |  | Not started | >= 90% intent accuracy on typed corpus | T3.1
T3.4 | T3 | Live mic -> intent end-to-end test | Parallel | 4 | 14 | 15 |  |  |  |  | Not started | Accuracy measured on live voice | T3.2, T3.3
T4.1 | T4 | Command validator + safety limits | Parallel | 6 | 16 | 17 |  |  |  |  | Not started | Out-of-range commands rejected in unit tests | T3.3
T4.2 | T4 | Intent -> MAVLink guided-mode mapping | Parallel | 8 | 17 | 19 |  |  |  |  | Not started | Every intent executes correctly in SITL | T2.2
T4.3 | T4 | Spoken command drives SITL flight end-to-end | Parallel | 4 | 20 | 20 |  |  |  |  | Not started | Voice -> simulated flight works (Gate G3)
T9.1 | T9 | LLM-based parser behind the same interface | Parallel | 8 | 31 | 34 |  |  |  |  | Not started | Passes the corpus in the same output format | Ethics decision: own voice vs participants
T9.2 | T9 | Compare parsers: accuracy, latency, robustness | Parallel | 8 | 35 | 38 |  |  |  |  | Not started | Comparison table for both parsers
T9.3 | T9 | Results tables + plots for the report | Parallel | 4 | 39 | 40 |  |  |  |  | Not started | Figures ready for report
T10.1 | T10 | Movement-accuracy trials against floor markers | Critical | 6 | 36 | 39 |  |  |  |  | Not started | Position error table (n >= 5 per command) | T8.2
T10.2 | T10 | End-to-end latency measurement (voice -> motion) | Critical | 4 | 40 | 41 |  |  |  |  | Not started | Latency mean / min / max recorded
T10.3 | T10 | Write report: method, results, evaluation | Critical | 12 | 42 | 48 |  |  |  |  | Not started | Full draft complete
T10.4 | T10 | Final review + submission prep | Critical | 3 | 49 | 50 |  |  |  |  | Not started | Submitted
|  | TOTAL |  | 210 |  |  | 33 |  |  |  | 6 of 35 done
Green cells mirror the Gantt sheet — edit plan and actual values there. Outcome and notes (blue) are editable here.

## Decision Gates
Decision Gates — planned vs actual day (linked to the Gantt sheet)
Gate | Subtask | Planned day | Actual day | Var (days) | Criterion | Action if not met
G1 | T1.4 | 5 | 5 | 0 | Outline, BOM and risk assessment approved; lab space confirmed | Revise scope or parts before further spending
G2 | T6.3 | 20 |  |  | Stable manual hover recorded | Extend tuning; escalate to supervisor
G3 | T4.3 | 20 |  |  | Voice command drives simulated flight | Hold hardware integration; fix software first
G4 | T7.4 | 30 |  |  | Hands-off position hold < 0.5 m drift, 5/5 trials (pivotal) | Demonstrate T8 in simulation; report hardware hold as a documented limitation
G5 | T8.2 | 35 |  |  | Voice sequence executes on the real drone | Base evaluation on simulation results
Slack: | The software strand is free from day 21 to day 30, so it can absorb slippage in the high-risk position-hold work (T7). Reporting runs to day 50, leaving roughly ten working days of contingency after the voice-control milestone (G5, day 35). Watch the Var column: a positive number on a critical-path task pushes everything after it.